## Construction schedule
Construction schedule |  |  | Renovation ¦ Gantt chart template
| Site | Enter site name | Start date | 2026-11-02
# | Work item | Crew | Start | Days | End
1 | Site protection | Cleaning / protection |  | 1
2 | Demolition | Demolition |  | 3
3 | Plumbing & electrical rough-in | Plumbing & electrical |  | 4
4 | Masonry (walls, plaster, waterproofing) | Masonry |  | 7
5 | Tiling | Masonry |  | 5
6 | A/C pipes + ducted indoor units | A/C |  | 2
7 | Carpentry (ceilings, partitions, cabinets) | Carpentry |  | 12
8 | Painting (filler, primer, topcoat) | Painting |  | 8
9 | Modular cabinet installation | Cabinets |  | 3
10 | Flooring | Flooring |  | 2
11 | Lights, switches & sockets | Plumbing & electrical |  | 2
12 | Curtains & wallpaper | Soft furnishings |  | 2
13 | Final cleaning | Cleaning |  | 1
14 | Inspection + snag fixes | Project manager |  | 3
| Total duration |  |  |  | days
How to use
Change the "Start date" above and the weekdays, dates and Gantt bars update across the whole sheet
Change the light-green "Days" and the following work items move back automatically
If two items overlap, edit that row's "Start" directly
Days are typical for a mid-size home renovation, weekends included. Adjust them for your site
Everywhere Design ¦ In the app, the schedule is this Gantt chart: shift the whole job when it slips, and crews see it on their phones everywhere-design.com