## Daily site log
Daily site log |  |  |  | Renovation ¦ one row per day
| Site | Enter site name |  |  | Client | Enter client | Start date | 2026-11-02 | This sheet from
Date | Day | Day no. | Weather | Crews on site | Workers | Work done today | Planned for tomorrow | Materials delivered / checked | Issues / to follow up | Recorded by
|  |  | Sunny | Protection, demolition | 4 | Lift, corridor and floor protection done Removed bathroom wall tiles and kitchen cabinets | Remove master bedroom wardrobe, haul away waste | 30 protection boards | Building management: corridor must be cleared by 17:30 | Site manager
|  |  | Cloudy | Demolition | 3 | Master bedroom wardrobe removed Two truckloads of waste hauled away | Plumber and electrician on site for setting out |  | Bathroom cold-water pipes corroded, photos taken, waiting for client to decide on full replacement | Site manager
|  |  | Rain | Plumbing & electrical | 2 | Kitchen & bathroom pipes set out Socket positions agreed with client | Pipework, pressure test | PVC pipe, cable | Client approved replacing all cold-water pipes; quote for the extra work tomorrow | Site manager
How to use
Enter the "Start date" above; "This sheet from" fills in, and the date, day and day number columns update automatically
Keep a row even on days with no work: write "Rained off" under weather or note the reason under issues, so you can look it up later
You can edit any date directly; the following days continue from it
The first three rows are examples; just type over them
One sheet per month: for the next month, duplicate the sheet and set "This sheet from" to the first day of the month; the day number carries on
Everywhere Design ¦ Crews check in by GPS on arrival so there is an automatic record, and site photos go straight into the site album everywhere-design.com